## Sheet1
WELLBEING RISKS (Psychological & Emotional)
Risk Area | Risk Description (Issue-Focused) | Likelihood | Severity | Risk Rating | Mitigation / Controls | Digital Tools | Maturity Scorecard Category
Psychological distress | Exposure to high-stress environments, conflict, or poor site culture leading to anxiety, burnout or mental ill-health | Possible | Major | High | • Identify psychosocial hazards in risk assessments • Early intervention pathways and support services • Supervisor capability training • Regular wellbeing check-ins (snapshot) | • Monthly Wellbeing Snapshot • Project Culture, Wellbeing and Flexibility Plan • External Support & Escalation Pathways Sheet | Reporting Systems Environment & Support Communication & Accountability
Suicide risk | Lack of awareness, stigma, or access to support increasing suicide risk among workers | Unlikely–Possible | Severe | High | • Partnerships with specialist providers (e.g. Mates, I Got You) • Visible support pathways on site • Toolbox talks focused on help-seeking | • Wellbeing Toolbox Talk Planner • Wellbeing Partnerships Framework (e.g. I Got You) • External Support & Escalation Pathways Sheet | Engagement Environment & Support Leadership
Exposure to traumatic events | Incidents, near misses or critical events impacting mental wellbeing | Possible | Major | High | • Critical incident response procedures • Post-incident support and debriefs • Access to professional support | • Project Culture, Wellbeing and Flexibility Plan • External Support & Escalation Pathways Sheet • Monitoring & Continuous Improvement Log | Environment & Support Innovation & Learning
Bullying & harassment | Poor behaviours creating psychological harm and unsafe work environments | Possible | Major | High | • Clear behavioural expectations • Reporting and escalation mechanisms • Leadership reinforcement and accountability | • Project Wellbeing & Time for Life Statement • Risk Matrix Addendum • Monthly Wellbeing Snapshot | Leadership Reporting Systems Accountability
TIME FOR LIFE RISKS (Fatigue, Workload & Balance)
Risk Area | Risk Description (Issue-Focused) | Likelihood | Severity | Risk Rating | Mitigation / Controls (Issue-Driven) | Digital Tools | Maturity Scorecard Category
Fatigue | Excessive hours, poor rostering or insufficient rest leading to impaired judgement and safety risks | Likely | Major | High | • Fatigue identified as a project risk • Work hour monitoring • Planning to avoid sustained excessive overtime | • Risk Matrix Addendum • Monthly Wellbeing Snapshot • Project Culture, Wellbeing and Flexibility Plan | Reporting Systems Organisational Goals Environment & Support
Presenteeism | Workers attending site while unwell due to job insecurity, workload pressure or culture | Possible | Moderate–Major | Medium–High | • Cultural reinforcement that health comes first • Supervisor awareness • Clear expectations communicated at start-up | • Project Wellbeing & Time for Life Statement • Monthly Wellbeing Snapshot • Toolbox Talk Planner | Leadership Communication & Accountability
Poor work–life balance | Ongoing imbalance contributing to burnout, disengagement and attrition | Likely | Moderate | High | • Realistic programming and resourcing • Regular review of workload pressures • Escalation pathways for emerging issues | • Monthly Wellbeing Snapshot • Monitoring & Continuous Improvement Log | Reporting Systems Innovation & Learning
Unrealistic deadlines | Program pressures driving unsafe behaviours or excessive workloads | Possible | Major | High | • Early risk identification in planning • Transparent conversations with clients • Leadership escalation where required | • Risk Matrix Addendum • Project Culture, Wellbeing and Flexibility Plan • Monitoring & Continuous Improvement Log | Organisational Goals Leadership Innovation & Learning
DIVERSITY & INCLUSION RISKS
Risk Area | Risk Description (Issue-Focused) | Likelihood | Severity | Risk Rating | Mitigation / Controls (Issue-Driven) | Digital Tools | Maturity Scorecard Category
Exclusionary site culture | Dominant behaviours or norms marginalising women, young workers, culturally diverse or LGBTQ+ workers | Possible | Major | High | • Clear behavioural standards • Inclusive leadership expectations • Targeted toolbox discussions | • Project Wellbeing & Time for Life Statement • Toolbox Talk Planner • Monthly Wellbeing Snapshot | Leadership Communication & Accountability Engagement
Discrimination or bias | Unequal treatment in access to work, development or progression | Unlikely–Possible | Major | Medium–High | • Transparent role allocation • Supervisor awareness training • Clear reporting mechanisms | • Risk Matrix Addendum • Project Culture, Wellbeing and Flexibility Plan • External Support & Escalation Pathways Sheet | Reporting Systems Accountability Environment & Support
Under-representation | Lack of diversity leading to isolation and retention challenges | Likely | Moderate | High | • Inclusive facilities and amenities • Mentoring and support initiatives • Visible leadership commitment | • Project Culture, Wellbeing and Flexibility Plan • Wellbeing Partnerships Framework | Organisational Goals Engagement
Inadequate facilities | Site amenities not suitable for diverse workforces (e.g. women, cultural needs) | Possible | Moderate | Medium | • Early planning of facilities • Consultation with workforce • Regular review and adjustment | • Risk Matrix Addendum • Monthly Wellbeing Snapshot | Reporting Systems Environment & Support
ADDITIONAL GOVERNANCE RISKS
Risk Area | Risk Description | Likelihood | Severity | Risk Rating | Mitigation | Digital Tools | Maturity Scorecard Category
“Compliance-only” implementation | Initiatives implemented without addressing underlying risks | Likely | Moderate | High | • Risk-led approach to CICS • Link controls directly to identified risks • Review effectiveness, not just activity | • CICS Risk Register (baseline) • Mapping of risks → controls → evidence | Leadership Innovation & Learning
Lack of visibility | Leadership commitment not translating to site-level behaviour | Possible | Major | High | • Start-up statements • Supervisor accountability • Regular monitoring | • Project Wellbeing & Time for Life Statement • Toolbox Talk Planner • Monthly Wellbeing Snapshot | Leadership Communication & Accountability
No feedback loop | Failure to learn from data, incidents or feedback | Possible | Moderate | Medium | • Monthly snapshot review • Continuous improvement log | • Monthly Wellbeing Snapshot • Monitoring & Continuous Improvement Log | Reporting Systems Innovation & Learning
NAWIC ACT Culture in Construction Digital Toolkit V1.0 Policies and Statements
Likelihood & Severity (example scale – adjustable)
Likelihood (L): Rare / Unlikely / Possible / Likely / Almost Certain
Severity (S): Minor / Moderate / Major / Severe
Risk Rating: Low / Medium / High / Extreme

## Sheet2 (hidden)
Practical Adoption Pathway – One Page Guide
Purpose
This pathway supports construction businesses to adopt the Culture in Construction Standard in a risk-led, practical and scalable way.
It focuses on identifying real issues first, then selecting proportionate controls and evidence — rather than implementing initiatives solely for compliance.
Level 1 — Foundation
Set expectations and identify real risks
Who this suits:
Organisations or projects beginning their CICS journey, or seeking a consistent baseline across projects.
Primary focus: Leadership ¦ Organisational Goals ¦ Reporting Systems
What you implement
Project Wellbeing & Time for Life Statement
CICS Risk Identification & Risk Matrix Addendum
Wellbeing
Time for Life
Diversity & Inclusion
What this addresses
Makes cultural expectations explicit from day one
Identifies genuine wellbeing, fatigue and inclusion risks
Embeds CICS into existing WHS and project risk systems
Evidence produced
Signed or communicated project statement
Updated project risk register including CICS risks
Maturity signal
“We understand our cultural risks and have leadership visibility over them.”
Level 2 — Embedded
Monitor, communicate and respond
Who this suits:
Projects or organisations with identified risks seeking to manage them proactively.
Primary focus: Communication & Accountability ¦ Environment & Support ¦ Reporting Systems
What you implement
Monthly Wellbeing Snapshot
Wellbeing Toolbox Talk Planner
External Support & Escalation Pathways Sheet
What this addresses
Early detection of fatigue, workload and psychosocial risks
Consistent, practical wellbeing conversations on site
Clear pathways for support and escalation
Evidence produced
Completed monthly snapshots
Toolbox delivery records
Visible support information on site
Maturity signal
“We actively monitor wellbeing risks and respond before they escalate.”
Level 3 — Mature
Learn, improve and lead
Who this suits:
Organisations seeking to demonstrate leadership and continuous improvement under CICS.
Primary focus: Innovation & Learning ¦ Engagement ¦ Leadership
What you implement
Project Wellbeing Plan
Wellbeing Partnerships Framework
Monitoring, Review & Continuous Improvement Log
What this addresses
Structured integration of wellbeing into project delivery
Specialist capability through external partnerships
Continuous learning based on real data and feedback
Evidence produced
Project-specific wellbeing plans
Partnership agreements or delivery records
Documented improvements and lessons learned
Maturity signal
“We learn from our data, adapt our approach, and influence positive culture beyond compliance.”
Key Principle
Controls and initiatives should always stem from identified risks.
Activities are not evidence of maturity unless they respond to real issues.
How to Use This Pathway
Progress at your own pace — not all projects need Level 3
Scale tools to suit project size and risk profile
Use the pathway to explain your approach to:
clients
workers
auditors
tender evaluators